## Test Plan
Requirements:
ID 1: Kinect connects ID 2: Grammar loads in ID 3: Player Behavior ID 4: Score System ID 5: Losing Condition ID 6: Final score/time displays ID 7: Menu Screens ID 8: Sound Controller ID 9: Pause Menu ID 10:Game resumes
Features to be tested:
TC.001: Kinect connects TC.002: Grammar loads in TC.003: Player Behavior TC.004: Score System TC.005:Losing Condition TC.006: Final score/time displays TC.007: Menu Screens TC.008: Sound Controller TC.009: Pause Menu TC.010: Game resumes
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Plan Objective: Test the Unity Game Shapes
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Kinect connects | When a level is run the ouput message "All players calibrated" will be shown. | 1. Launch any level 2. Notice the log statement | Kinect is plugged in and functional | "All players calibrated" will be shown in the log | "All players calibrated" message appeared | Pass
2 | 1 | TC.002 | Grammar loads in | When a level is run the ouput message "Recogniser running" will be shown. | 1. Launch any level 2. Notice the log statement | Methods for the Grammar Recogniser is error free | "Recogniser running" will be shown in the log | "Recogniser running" message appeared | Pass
3 | 1 | TC.003 | Player Behavior | Player behavior working as intended. | 1. Launch any level. 2. Use arms to control the two objects | Objects are connected to the script Kinect Overlayer | The player should be able to move the objects around the bounds of the screen. | Player movement is working as intended. | Pass
4 | 1 | TC.004 | Score system | When the player passes a barrier the score will increase | 1.Launch any level. 2.wait for barrier 3.Attempt to pass barrier 4. Check if the score increases. | The UI text is linked to the score counter. | When the player passes the barrier the score increases. | Score counter is working as intended. The UI text is updating. | Pass
5 | 1 | TC.005 | Losing Condition | If the players hearts reaches 0 the game stops | 1.Launch any level. 2.Move objects infront of barriers 3. Notice if the players hearts reaches 0. | The hearts system is working correctly. | When the players hearts reaches 0 the game will stop. | Game stops and end level UI is shown. | pass
6 | 1 | TC.006 | Final score/time displays | When the player runs out of hearts the final score and time will be shown. | 1.Launch any level. 2.Build up score and time 3. When the end level UI shows, check score and time | The end level UI contains the UI Text objects | When the player runs out of hearts the final score and time will be shown. | When the player runs out of hearts the final score and time shows. | Pass
7 | 1 | TC.007 | Menu Screens | The user can navigate the game using voice | 1. Launch the game. 2. Say all phrases linked with the menus. | All scenes are in the build settings.The switch statement is linked to correct methods. | When a user says a phrase like "go to level select" the scene changes | Menu navigation is working as intended. | Pass
8 | 1 | TC.008 | Sound Controller | The sound is working and can be altered via Voice | 1. Launch the game. 2. Test the sound settings by saying "turn sound on" or "turn sound off" | The Audio is working as intended. | When the user says either phrase the sound will be altered. | The sound is turned of when user says "Turn sound off" Sound is turned on by the phrase "Turn sound on" | Pass
9 | 1 | TC.009 | Pause Menu | When the user says "pause the game" the game stops and the pause menu appears. | 1. Launch any level. 2. Say "pause the game" | The switch statement is linked to correct methods. | When the user says "pause the game" the pause menu launches. | The pause menu appears and game is paused when user says "pause the game". | Pass
10 | 1 | TC.010 | Game resumes | When the user is in the pause menu and says "resume the game" the game resumes as normal. | 1. Launch any level. 2. Say "Pause the game" 3. Pause menu appears. 4. Say "resume the game". | The switch statement is linked to correct methods. | When the user says "resume the game" in the pause menu the game resumes. | The game resumes from the point at which the user says "pause the game". | Pass